## PracticeStartup
ORGANIZATION NAME : | Practice Start Up List: This is being provided as a reference of items to think about when opening or relocating a medical practice. The list below is not conclusive as there may be other items that need to be tended to.
Task | Associated TaskList | Assigned To | Resources Needed To Complete Task | Start Date | Due Date | Date Completed | Priority | Status | Notes
Implement HIPAA compliance program | Compliance Issues
Implement OSHA compliance program | Compliance Issues
Implement Stark compliance program | Compliance Issues
Train staff in universal precautions | Compliance Issues
Coordinate conversion | Computer/Software Selection
Coordinate demonstrations | Computer/Software Selection
Coordinate installation | Computer/Software Selection
Coordinate system set-up (e.g. Payer codes, payer classes) | Computer/Software Selection
Define hardware & software requirements (e.g. PPM, EMR, imaging) | Computer/Software Selection
Evaluate proposals | Computer/Software Selection
Finalize computer training schedule and implementation timeline | Computer/Software Selection
Make sure all employees are adequately trained on new computer system | Computer/Software Selection
Negotiate purchase agreement | Computer/Software Selection
Negotiate service agreement | Computer/Software Selection
Prepare requests for proposal | Computer/Software Selection
Select qualified vendors | Computer/Software Selection
Complete and mail managed-care provider applications or notify for existing practice | Credentialing and Privileging Issues
Determine present participation in plans & hospital privileges | Credentialing and Privileging Issues
Submit applications for hospital privileges | Credentialing and Privileging Issues
Update federal narcotic license | Credentialing and Privileging Issues
Update managed-care provider notify of change in provider status | Credentialing and Privileging Issues
Update Medicare and Medicaid provider application | Credentialing and Privileging Issues
Update membership in county medical society | Credentialing and Privileging Issues
Update membership in state medical association | Credentialing and Privileging Issues
Update NPI Listing | Credentialing and Privileging Issues
Update state medical license | Credentialing and Privileging Issues
Update state narcotic license | Credentialing and Privileging Issues
Conduct CPT and ICD-9 training | Fees and Coding
Develop hospital charge ticket, if applicable | Fees and Coding
Develop office charge ticket | Fees and Coding
Development of practice fee schedule | Fees and Coding
Employee CPT training meeting | Fees and Coding
Order CPT and ICD-9 book | Fees and Coding
Order speciality specific coding book(s) | Fees and Coding
Physician CPT training meeting | Fees and Coding
Review usage of evaluation & management codes | Fees and Coding
Telephone survey of selected fees | Fees and Coding
Coordinate merchant credit card account | Financial Planning, Accounting and Billing Issues
Decide on petty cash policy | Financial Planning, Accounting and Billing Issues
Determine banking services needed | Financial Planning, Accounting and Billing Issues
Determine loan financing requirements | Financial Planning, Accounting and Billing Issues
Employee bank reconciliation training | Financial Planning, Accounting and Billing Issues
Negotiate loan/services | Financial Planning, Accounting and Billing Issues
Obtain competitive bids | Financial Planning, Accounting and Billing Issues
Open practice checking account | Financial Planning, Accounting and Billing Issues
Order patient account statement | Financial Planning, Accounting and Billing Issues
Prepare and review personal financial statement | Financial Planning, Accounting and Billing Issues
Prepare cash flow projection | Financial Planning, Accounting and Billing Issues
Prepare furniture & equipment budget (see location planning above) | Financial Planning, Accounting and Billing Issues
Prepare loan request summary | Financial Planning, Accounting and Billing Issues
Present loan summary to banking institutions | Financial Planning, Accounting and Billing Issues
Schedule testing of Medicare/Medicaid electronic billing | Financial Planning, Accounting and Billing Issues
Select banks to submit loan request | Financial Planning, Accounting and Billing Issues
Select collection agency | Financial Planning, Accounting and Billing Issues
Select credit card processor | Financial Planning, Accounting and Billing Issues
Set up practice internal controls | Financial Planning, Accounting and Billing Issues
Set up Quickbooks system and related training | Financial Planning, Accounting and Billing Issues
Coordinate with pharmaceutical representatives | Forms & Supplies
Create Account with Medical Supply company (Medline, McKesson, etc) | Forms & Supplies
Draft new patient information form | Forms & Supplies
Obtain office supplies | Forms & Supplies
Order HCFA forms | Forms & Supplies
Order initial stock of medical supplies | Forms & Supplies
Order Medicaid manual | Forms & Supplies
Order Medicare manual | Forms & Supplies
Evaluate hospital support packages | Hospital Support Package
Negotiate hospital support packages | Hospital Support Package
Solicit hospital support packages | Hospital Support Package
Evaluate any med/mal "tail" issues | Insurance Needs
Evaluate insurance needs | Insurance Needs
Obtain employee fidelity bond coverage for retirement plan | Insurance Needs
Obtain quotes and purchase dental insurance | Insurance Needs
Obtain quotes and purchase Employee Practices Liability | Insurance Needs
Obtain quotes and purchase group health insurance | Insurance Needs
Obtain quotes and purchase office liability insurance | Insurance Needs
Obtain quotes and purchase Workers' Comp insurance | Insurance Needs
Obtain/Transfer Disability Insurance Coverage | Insurance Needs
Obtain/Transfer Life Insurance Coverage | Insurance Needs
Obtain/Transfer Malpractice Coverage | Insurance Needs
Select agents to submit proposals | Insurance Needs
Apply for state and local tax identification numbers | Legal
Register with Secretary of State | Legal
Coordinate entity name reservation | Legal
Obtain federal tax I.D. number | Legal
Selection of Entity and Entity Formation | Legal
Complete room by room fixed asset needs list | Location Analysis and Space Planning
Conduct location analysis | Location Analysis and Space Planning
Construction administration | Location Analysis and Space Planning
Coordinate Move-In | Location Analysis and Space Planning
Coordinate Signage | Location Analysis and Space Planning
Design office layout | Location Analysis and Space Planning
Determine space requirements | Location Analysis and Space Planning
Evaluate space plans | Location Analysis and Space Planning
Execute office lease | Location Analysis and Space Planning
Interior Design | Location Analysis and Space Planning
Negotiate lease terms | Location Analysis and Space Planning
Obtain Competitive Bids | Location Analysis and Space Planning
Office lease reviewed by legal counsel | Location Analysis and Space Planning
Prepare construction documents | Location Analysis and Space Planning
Review Owner-Contractor Agreement | Location Analysis and Space Planning
Select location | Location Analysis and Space Planning
Basic brochure development | Marketing
Coordinate design and placement of newspaper ad | Marketing
Coordinate development of practice logo | Marketing
Coordinate development of yellow pages ad | Marketing
Coordinate letterhead/business card design | Marketing
Develop advertising budget | Marketing
Draft announcement card | Marketing
Draft practice marketing plan | Marketing
If specialist, meet with referring doctors | Marketing
Mail out announcement cards | Marketing
Obtain web address | Marketing
Order announcement cards | Marketing
Order business cards | Marketing
Order office stationery | Marketing
Order patient info booklet | Marketing
Other direct mail or advertising? | Marketing
Place order for white pages | Marketing
Plan details of open house | Marketing
Practice Logo | Marketing
Purchase office opening announcement in newspaper | Marketing
Select list of referring doctors | Marketing
Select open house date | Marketing
Website Design Plans | Marketing
Website Development | Marketing
Credentialing | Miscellaneous
Exam Room Furniture | Miscellaneous
Office Furniture | Miscellaneous
Triage Protocols- PMI Recommends ClearTriage.com | Miscellaneous
Triage Service | Miscellaneous
Waiting Room Furniture | Miscellaneous
Arrange for physician coverage | Miscellaneous Issues
Contract with transcription service | Miscellaneous Issues
Employee computer training status | Miscellaneous Issues
Implement CLIA compliance if applicable | Miscellaneous Issues
Order reception room periodicals | Miscellaneous Issues
Select outside reference lab | Miscellaneous Issues
Evaluate initial month end | Office Operational Issues
Finalize financial statement format | Office Operational Issues
Observe staff during first day of operations | Office Operational Issues
Prepare office policy and procedures manual | Office Operational Issues
Set-up accounts payable procedures | Office Operational Issues
Set-up adjustment guidelines | Office Operational Issues
Set-up appointment scheduling guidelines | Office Operational Issues
Set-up bank deposit guidelines | Office Operational Issues
Set-up billing and accounts receivable follow-up guidelines | Office Operational Issues
Set-up daily financial close out procedures | Office Operational Issues
Set-up daily/monthly financial reporting | Office Operational Issues
Set-up financial policies | Office Operational Issues
Set-up hospital charge accumulation guidelines | Office Operational Issues
Set-up office charge accumulation guidelines | Office Operational Issues
Set-up periodic audit schedule | Office Operational Issues
Set-up time of service collection guidelines | Office Operational Issues
Train staff in business procedures prior to opening | Office Operational Issues
Evaluate organizational options | Organizational and Physician Issues
Finalize and execute recruitment contract, if applicable | Organizational and Physician Issues
Negotiate withdrawal from existing practice, if applicable | Organizational and Physician Issues
Physician Compensation Model and Employment Agreements, if group practice | Organizational and Physician Issues
Select a date to begin practice | Organizational and Physician Issues
Select Accountant | Organizational and Physician Issues
Select Legal Services Provider | Organizational and Physician Issues
Selection of Entity Name | Organizational and Physician Issues
Structure Buy/Sell Agreement, if group practice | Organizational and Physician Issues
Structure Employment Agreement | Organizational and Physician Issues
Coordinate review of instruments/smaller items | Other Equipment Planning
Determine acquisition schedule | Other Equipment Planning
Evaluate bids | Other Equipment Planning
Obtain quotes and order photocopier, typewriter, fax machine | Other Equipment Planning
Obtain quotes/order examination room equipment | Other Equipment Planning
Obtain quotes/order furniture items (e.g. waiting room, MD office) | Other Equipment Planning
Obtain quotes/order laboratory equipment | Other Equipment Planning
Obtain quotes/order other clinical equipment | Other Equipment Planning
Obtain quotes/order refrigerator, microwave, breakroom furniture | Other Equipment Planning
Obtain quotes/order transcription equipment | Other Equipment Planning
Order medical record filing system | Other Equipment Planning
Order office furniture | Other Equipment Planning
Prepare furniture & equipment budget | Other Equipment Planning
Prepare purchase orders/ Coordinate deposits | Other Equipment Planning
Review Needs | Other Equipment Planning
Submit major items for bid | Other Equipment Planning
Background check | Personnel and Benefit Issues
Check references on selected finalists | Personnel and Benefit Issues
Coordinate payroll services | Personnel and Benefit Issues
Determine employee benefit package | Personnel and Benefit Issues
Determine staff positions | Personnel and Benefit Issues
Develop job descriptions | Personnel and Benefit Issues
Develop organizational chart | Personnel and Benefit Issues
Develop personnel policy manual (PPM) | Personnel and Benefit Issues
Employee meeting to review and discuss policy manual and office operations | Personnel and Benefit Issues
Interview job candidates | Personnel and Benefit Issues
Make job offer | Personnel and Benefit Issues
Prepare and place advertisements for new employees | Personnel and Benefit Issues
Prepare employee personnel files | Personnel and Benefit Issues
Prepare employment acceptance letter | Personnel and Benefit Issues
Review resumes | Personnel and Benefit Issues
Specify salary schedule | Personnel and Benefit Issues
Telephone screening of candidates | Personnel and Benefit Issues
Coordinate installation of lines | Telephone System Selection/Communications
Coordinate remote call forwarding | Telephone System Selection/Communications
Define hardware needs (e.g. voice mail) | Telephone System Selection/Communications
Determine lines/features needed (e.g. cable modem/DSL) | Telephone System Selection/Communications
Evaluate bids | Telephone System Selection/Communications
Obtain telephone number | Telephone System Selection/Communications
Order equipment | Telephone System Selection/Communications
Select answering service | Telephone System Selection/Communications
Select paging service | Telephone System Selection/Communications
Select vendors for bids | Telephone System Selection/Communications